## Minh
Project ERP
Status | Department |  | Project | Time(h) | Date Finished
Estimate | PLN | 1 | Sửa lại chức năng Hold Function | 42 | 2013-12-12
Estimate | PLN | 2 | Sửa lại luồng tạo SO (Khác Revision đối với hàng internal PO)
Estimate | PLN | 3 | Second WO
Coding | PLN | 4 | Cancel WO | 63 | 2013-11-26
Coding | PLN | 5 | Tách WO, cùng Revision | 70 | 2013-11-03
Coding | PLN | 6 | Increase WO | 49 | 2013-11-22
Estimate | PLN | 7 | Do Du Lieu Qty In(Kết tháng theo ITW) | 5 | 2014-01-21
Estimate | PUR | 8 | Link dữ liệu đổi mã veneer code (1-1)
Estimate | PUR | 9 | Veneer report theo độ dài, độ rộng
Estimate | PUR | 10 | KPI PR thêm reason
Estimate | PLN | 11 | Test link dữ liệu Hold (Master Plan) | 7 | 2013-12-12
Estimate | PLN | 12 | Test tòan bộ Master Plan | 50 | 2014-01-21
Finished | PLN | 13 | Đổ dữ liệu WIP Process CAR | 4 | 2013-11-19
Estimate | PLN | 14 | Khi nhận Enquiry phải có thông tin WO
Finished | PLN | 15 | Do Du Lieu WO Qty | 2 | 2013-11-19
Estimate | PAK | 16 | Ngan chan lai Box Va Furniture Khac WO
Finished | PAK | 17 | Report cho IT theo doi tien do | 8 | 2013-11-18
Finished | PAK | 18 | Print Packing với mode la William | 2 | 2013-11-19
Estimate | ACC | 19 | Chỉnh lại công thức FOB phần giá cho Huơng ACC
Finished | WHD | 20 | Tao Request Online Cho Veneer Truoc khi co Stock Balance | 1 | 2013-11-19
Estimate | PUR | 21 | Add thêm thông tin material khi in PR Online | 2 | 2013-11-22
Estimate | PLN | 22 | Export Excel (PR Online) format lại định dạng ngày tháng | 1 | 2013-11-22
Estimate | PLN | 23 | Email Auto khi cancel, hoặc return đối với chức năng PR Online | 8 | 2013-11-22
Estimate | CSD | 24 | Royaty Fee của Designer, đã thảo luận với Bruss
Estimate | PLN | 25 | Tao nút Finish đối với Supplement (Material, Veneer, Woods )
Estimate | ACC | 26 | Export Excel với WIP COM1 Value Actual Price Report | 10 | 2014-01-17
Estimate | PLN | 27 | Closing WO (Material Code), Add Consumed WO Cho Veneer, Woods | 15 | 2013-12-20
Estimate | PLN | 28 | PR Follow Up report | 4 | 2013-12-10
Finished | ACC | 29 | Chinh lai phan Value Point (factory Actual Price) capture du lieu | 4 | 2013-11-25
Finished | PLN | 30 | Test SO Cancel (Create Internal PO) | 3 | 2013-11-26
Finished | PLN | 31 | User Guide For Cancel | 18 | 2013-11-26
Estimate | FOU | 32 | Material Foudry | 5 | 2013-12-12
Estimate | FOU | 33 | Deadline Foundry
Estimate | CSD | 34 | Cancel SO with Diff Price
Estimate | CSD | 35 | Prevent SO Custom with Don’t check fix price | 1 | 2013-12-19
Estimate | PLN | 36 | WO(Sample, Inhouse, Subcon)
Estimate | PUR | 37 | PO Received A Part, Muốn Cancel và làm lại PO mới của cùng PR | 2 | 2013-12-12
Estimate | PUR | 38 | Update Expect Date của PR | 30 | 2014-01-08
Estimate | PLN | 39 | Material Packing Calculate From Deadline | 10 | 2014-01-08
Estimate | PLN | 40 | Tach ID Veneer 2 barcode | 20 | 2013-12-18
Estimate | PLN | 41 | Chinh sua lai phan Cancel WO Guide Hong Anh(PLN)
Estimate | CSD | 42 | To Mau Cancel Enquiry (Voi Field la Cancel) | 1 | 2013-12-20
Estimate | PLN | 43 | Sua Email Cancel tu dong cho Thao PLN
Estimate | IT1 | 44 | Bao Email tu dong, bao lich lam viec ngay truoc cho IT Mailling | 4 | 2013-12-14
Estimate | PRO | 45 | Carcass WO - Jakob
Estimate | ACC | 46 | Capture Data WIP COM 1 | 5 | 2014-01-08
Estimate | ACC | 47 | Cost Price For Carcass Code (ITW)
Estimate | PLN | 48 | Deadline WO(Customize Toan bo luong)
Estimate | PLN | 49 | Chinh sua store WIP Status vao trong Master Plan Container
Estimate | PLN | 50 | Bo Balance SO (Balance - Holded) Man hinh SO Not Yet Put On Container | 0.5 | 2014-01-08
Estimate | ACC | 51 | Ngoc BOD Report Value Point As Thanh ACC Request
Estimate | PLN | 52 | Thao PLN (Add man hinh get thong tin cancel vao change request Date)
Estimate | IT1 | 53 | Report theo doi task IT request From Mr Chau
Estimate | CAR | 54 | Check Data Process Carcass For Allen | 16 | 2014-01-08
Estimate | IT1 | 55 | Chinh sua cach tinh IT Project (Cong vao phep ngay nghi bu) | 2 | 2014-01-17
Estimate | PLN | 56 | Item Shipped As Ngoc Request
Estimate | ACC | 57 | Report CST Full Set For Mr Thanh
Estimate | PUR | 58 | Chinh lai phan thong bao email khi gui email hang ngay cho Purchasing and Requester
Estimate | PLN | 59 | Add thêm 1 cột Box ID for MrNam, Report FGW
Estimate | PLN | 60 | Chinh sua module ItemGroup cho Planning với default Customer
Estimate | PUR | 61 | Chinh sua PR Change Expect Date
Estimate | PLN | 62 | Sua lai chuc nang combine ItemCode
Estimate | PLN | 63 | Chinh sua container wip status report, cho chon nhiu container
Estimate | PUR | 64 | Report lay consumption Material cho Jakob
Estimate | PLN | 65 | Chinh lai WIpStatus, Neu Carcass Code = 'CAR-00000-A' thi tinh hang nam o FOU
Estimate | PLN | 66 | Chỉnh sửa report container, 2 option với sản xuất và Planning

## Tron
No | Status | Department | Project | Time(h) | Finished Date | Pending
1 | Estimate | TEC | Allow user to add "Revision record" for the attached item list | 4 |  | Testing
2 | Coding | Jakob | Balance CBM beetwen Keynumbers & MCH Planning output | 4 |  | Coding
3 | Pending | COM1 | Auto clear stock balance of components in COM1 when parent component is transfered full set or carcass is transfered in ITW fullset | 3 | 2014-01-14 | Estimate
4 | Estimate | COM1 | Create COM1 WIP Report | 4 |  | Finished
5 | Pending | ACC | Create Aging Receivable Detail Report | 4
6 | Testing | Antony | Capture Item Cost Price as Antony request | 14 | 2014-01-21
7 | Estimate | PUR | Carcass price comparison | 4
8 | Estimate | ACC | Outstanding Debit Note Report | 4
9 | Estimate | ACC | Outstanding Invoice Report | 4
10 | Estimate | ACC | Outstanding Pro Forma Invoice Report | 4
11 | Estimate | ACC | Distribute credit note into Invoice | 7
12 | Estimate | ACC | Chose period and add column in the summary of Liabilities from Customers Report | 4
13 | Estimate | MAR | Delete Related & Alternative for discontinue Items function | 14 | 2014-01-28
14 | Testing | MAR | Add Marketing Name in Finishing Group and link it to report JC ERP product for Website & Product data file | 10 | 2014-01-27
15 | Estimate | MAR | Add column Description on Collection List & Category List | 14 | 2014-01-28
16 | Estimate | COM1 | Search multi deadline for COM1 | 14
17 | Estimate | CAR | Reuse the old part barcode when adjust out | 7
18 | Estimate | CAR | The way part code go (work area) | 7
19 | Estimate | QC | QC Transaction of carcass & com1 | 40
20 | Estimate | PLN | Planning point - to receive any qty from subcont to deliver to other dept beside production (like QC, Tech, .) and adjustment qty from system | 21
21 | Estimate | WH | Return function to Subcont | 10
22 | Estimate | CAR | Manage repair, return item | 28
23 | Estimate | CAR | How to scan mirror frame | 14
24 | Estimate | IT | Check costing of item if it changed & save history | 7
25 | Estimate | COM2 | Processing Schedule for COM2 | 14 | 2014-01-14
26 | Coding | COM2 | Cost Price For Component | 14 | 2014-01-28
27 | Not Analyse | PLN | Look Up Available
28 | Finished | PLN | ASS Month To Date Output Report | 7 | 2014-01-27